## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Problem statement discussion & scenario selection (vendor pricing, job offer, project budget) | MUST HAVE | No Dependency | All | 3- Completed
S1 | S1 | US-002 | Project architecture and negotiation flow design | MUST HAVE | No Dependency | All | 3- Completed
S1 | S1 | US-003 | Define scenario templates - agents, roles, goals, constraints | MUST HAVE | No Dependency | Madhugna | 3- Completed
S1 | S1 | US-004 | Build agent configuration screen (personality selection, goal display) | MUST HAVE | No Dependency | Madhugna | 3- Completed
S1 | S1 | US-005 | Design orchestration flow and negotiation state model | MUST HAVE | No Dependency | Madhugna | 3- Completed
S1 | S1 | US-006 | Study LLM-based agent reasoning patterns; design persona model | MUST HAVE | No Dependency | Tharun Gowda | 3- Completed
S1 | S1 | US-007 | Define objective satisfaction scoring per scenario | SHOULD HAVE | No Dependency | Prasad | 3- Completed
S1 | S1 | US-008 | Wireframe Negotiation Arena UI (chat transcript + metrics panel) | MUST HAVE | No Dependency | Bhagyashree | 2- In Progress
S1 | S1 | US-009 | Wireframe Human Participant Interface (Practice Mode) | MUST HAVE | No Dependency | Sree Priya | 3- Completed
S2 | S2 | US-010 | Refine agent configuration screen from integration feedback | SHOULD HAVE | Orchestrator interface | Madhugna | 3- Completed
S2 | S2 | US-011 | Build Orchestrator Agent (turn order, history passing, state/round tracking) | MUST HAVE | Persona schema | Madhugna | 3- Completed
S2 | S2 | US-012 | Lead end-to-end AI vs AI testing (all 3 scenarios) | MUST HAVE | Orchestrator build | Harshita | 3- Completed
S2 | S2 | US-013 | Build LLM reasoning / offer generation engine | MUST HAVE | Orchestrator turn-handling interface | Tharun Gowda | 3- Completed
S2 | S2 | US-014 | Test reasoning engine across all 3 scenario templates | MUST HAVE | US-013 | Tharun Gowda | 3- Completed
S2 | S2 | US-015 | Build Counteroffer Evaluation & Concession Module | MUST HAVE | Orchestrator turn-handling interface | Prasad | 3- Completed
S2 | S2 | US-016 | Build static/mock transcript view (sample data) | MUST HAVE | No Dependency | Bhagyashree | 3- Completed
S2 | S2 | US-017 | Build Practice Mode scaffolding | SHOULD HAVE | Orchestrator turn-handling interface | Sree Priya | 3- Completed
S3 |  | US-018 | Build Deadlock Detection & Resolution module | MUST HAVE | Orchestrator state tracking | Harshita | 2- In Progress
S3 |  | US-019 | Tune reasoning quality against Practice Mode inputs | SHOULD HAVE | Practice Mode build | Tharun Gowda | 2- In Progress
S3 |  | US-020 | Full Practice Mode build (human offers, real-time AI reactions) | MUST HAVE | Reasoning engine | Sree Priya (unwell) - covered by Madhugna, Prasad, Bhagyashree | 2- In Progress
S3 |  | US-021 | Support Practice Mode validation (concession logic vs human input) | SHOULD HAVE | US-020 | Prasad | 2- In Progress
S3 |  | US-022 | Wire up live agent turns, reasoning display, stance indicators, round metrics | MUST HAVE | Orchestrator build | Madhugna | 2- In Progress
S4 | S4 | US-023 | Build Outcome Screen - final agreement terms, concession timeline, rounds elapsed, per-agent objective satisfaction score | MUST HAVE | No Dependency | Bhagyashree | 3- Completed
S4 | S4 | US-024 | Connect Outcome Screen with existing evaluation data | MUST HAVE | US-023 | Bhagyashree | 3- Completed
S4 | S4 | US-025 | Improve Practice Mode UI - chat-focused layout, config moved to side panel, more conversational human input/decision-making | MUST HAVE | No Dependency | Sree Priya | 3- Completed
S4 | S4 | US-026 | Review and improve Human -> Orchestrator -> Prompt Builder -> AI Agent flow | MUST HAVE | No Dependency | Sree Priya | 3- Completed
S4 | S4 | US-027 | Implement downloadable negotiation transcript and summary report | MUST HAVE | US-023 | Sree Priya | 3- Completed
S4 | S4 | US-028 | End-to-end testing of AI-vs-AI and Practice Mode across all 3 scenarios (Flood, Earthquake, Cyclone) and personality combinations | MUST HAVE | All modules complete | Bhagyashree | 3- Completed
S4 | S4 | US-029 | Test Outcome Screen, downloads, and Practice Mode changes; check consensus, deadlock, and regression issues; fix integration issues found | MUST HAVE | US-023, US-025, US-027 | Bhagyashree | 3- Completed
S3 |  | US-030 | Testing support across Sprint 3 modules (Practice Mode, Deadlock Detection) | SHOULD HAVE | No Dependency | Bhagyashree, Tharun Gowda | 3- Completed
S3 |  | US-031 | Agile tracker documentation update | SHOULD HAVE | No Dependency | Bhagyashree | 3- Completed
S4 | S4 | US-032 | Agile tracker progress updates across all 4 milestones | MUST HAVE | No Dependency | Bhagyashree | 3- Completed
S4 | S4 | US-034 | Extend downloadable Transcript & Summary Report functionality to AI-vs-AI mode (previously Practice Mode only) | MUST HAVE | US-027 | Madhugna | 3- Completed
S4 | S4 | US-033 | Milestone 4 technical report compilation | MUST HAVE | No Dependency | Bhagyashree | 3- Completed
S4 | S4 | US-035 | Verify updated AI-vs-AI & Practice Mode flows post-M4 (Outcome screen, consensus, final allocation, concession analysis) | MUST HAVE | US-023, US-025 | Bhagyashree, Madhugna | 3- Completed
S4 | S4 | US-036 | Push milestone4-progress branch to main; update README | SHOULD HAVE | No Dependency | Madhugna, Harshitha | 3- Completed
S4 | S4 | US-037 | Test M4 Part 2 (Practice Mode) - verify chat-first UI, side panel, downloadable transcript/summary | SHOULD HAVE | US-025, US-027 | Prasad | 3- Completed
S5 | S5 | US-038 | Implement MongoDB persistence (Motor/PyMongo); create /api/history endpoints for negotiation storage/deletion; set up history UI integration | MUST HAVE | No Dependency | Harshita | 3- Completed
S5 | S5 | US-039 | Complete accompanying UI changes for history/DB integration | MUST HAVE | US-038 | Harshita | 3- Completed
S5 | S5 | US-040 | Fix MongoDB persistence issues; test negotiation/history APIs | MUST HAVE | US-038 | Madhugna | 3- Completed
S5 | S5 | US-041 | Implement History -> Negotiation Arena read-only replay, historical outcome, and report/summary downloads | MUST HAVE | US-038 | Madhugna | 3- Completed
S5 | S5 | US-042 | Improve UI - Current Proposal table, Available Resources, History/Replay flow, AI provider branding | SHOULD HAVE | US-041 | Madhugna | 3- Completed
S5 |  | US-043 | Postman testing of APIs on current main version | SHOULD HAVE | US-038 | Madhugna, Prasad | 3- Completed
S5 |  | US-044 | Continue testing while DB integration work is added | SHOULD HAVE | US-038 | All | 3- Completed
S5 |  | US-045 | Prepare overall project report | MUST HAVE | No Dependency | Tharun Gowda | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours. Yellow cells = fill in your actual dates/hours.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 256.5 | 153 | 72.5 | 20 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Problem statement discussion & scenario selection | 2026-07-29 | 2026-07-29 | All | Others | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Architecture and negotiation flow design | 2026-07-31 | 2026-07-31 | All | Design | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Define scenario templates - agents, roles, goals, constraints | 2026-08-02 | 2026-08-02 | Madhugna | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Build agent configuration screen | 2026-08-04 | 2026-08-05 | Madhugna | Build | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Design orchestration flow and negotiation state model | 2026-08-06 | 2026-08-07 | Madhugna | Design | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Study LLM-based agent reasoning patterns; design persona model | 2026-08-07 | 2026-08-08 | Tharun Gowda | Others | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | Define objective satisfaction scoring per scenario | 2026-08-07 | 2026-08-07 | Prasad | Design | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 8 | Wireframe Negotiation Arena UI | 2026-08-07 | 2026-08-07 | Bhagyashree | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 9 | Wireframe Human Participant Interface (Practice Mode) | 2026-08-07 | 2026-08-07 | Sree Priya | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-010 | 10 | Refine agent configuration screen from integration feedback | 2026-08-11 | 2026-08-11 | Madhugna | Coding | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 11 | Build Orchestrator Agent (turn order, history, state/round tracking) | 2026-08-13 | 2026-08-15 | Madhugna | Build | 3- Completed | 10 | 3.5 | 3.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 12 | Lead end-to-end AI vs AI testing (all 3 scenarios) | 2026-08-15 | 2026-08-16 | Harshita | System Test | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 13 | Build LLM reasoning/offer generation engine | 2026-08-11 | 2026-08-13 | Tharun Gowda | Build | 3- Completed | 10 | 3.5 | 3.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 14 | Test reasoning engine across all 3 scenario templates | 2026-08-19 | 2026-08-19 | Tharun Gowda | Integration Test | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | Build Counteroffer Evaluation & Concession Module | 2026-08-16 | 2026-08-18 | Prasad | Build | 3- Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 16 | Build static/mock transcript view (sample data) | 2026-08-23 | 2026-08-24 | Bhagyashree | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 17 | Build Practice Mode scaffolding | 2026-08-11 | 2026-08-12 | Sree Priya | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010b | 18 | Frontend negotiation UI - per-district resource cards formatting | 2026-08-27 | 2026-08-27 | Harshita | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-018 | 19 | Build Deadlock Detection & Resolution module | 2026-08-29 | 2026-08-30 | Harshita | Build | 2- In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 20 | Tune reasoning quality against Practice Mode inputs | 2026-08-31 | 2026-09-01 | Tharun Gowda | Coding | 2- In Progress | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 21 | Full Practice Mode build (human offers, real-time AI reactions) | 2026-09-02 | 2026-09-02 | Sree Priya | Build | 2- In Progress | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | 22 | Support Practice Mode validation (concession logic vs human input) | 2026-09-04 | 2026-09-04 | Prasad | Integration Test | 2- In Progress | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | 23 | Wire up live agent turns, reasoning display, stance indicators, round metrics | 2026-09-06 | 2026-09-07 | Bhagyashree | Coding | 2- In Progress | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 24 | Cover Practice Mode build for Sree Priya (unwell) | 2026-09-06 | 2026-09-07 | Madhugna, Prasad, Bhagyashree | Build | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-030 | 25 | Testing support across Sprint 3 modules | 2026-09-06 | 2026-09-06 | Bhagyashree, Tharun Gowda | System Test | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-031 | 26 | Agile tracker documentation update | 2026-09-06 | 2026-09-06 | Bhagyashree | Others | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-023 | 27 | Build Outcome Screen - final agreement terms, concession timeline, rounds elapsed, per-agent score | 2026-09-10 | 2026-09-13 | Bhagyashree | Build | 3- Completed | 10 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | 28 | Connect Outcome Screen with existing evaluation data | 2026-09-10 | 2026-09-13 | Bhagyashree | Integration Test | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | 29 | Improve Practice Mode UI - chat-focused layout, config moved to side panel | 2026-09-10 | 2026-09-11 | Sree Priya | Design | 3- Completed | 5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | 30 | Review and improve Human -> Orchestrator -> Prompt Builder -> AI Agent flow | 2026-09-10 | 2026-09-11 | Sree Priya | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-027 | 31 | Implement downloadable negotiation transcript and summary report | 2026-09-10 | 2026-09-11 | Sree Priya | Build | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-028 | 32 | End-to-end testing: AI-vs-AI & Practice Mode across Flood/Earthquake/Cyclone scenarios and personality combinations | 2026-09-10 | 2026-09-13 | Bhagyashree | System Test | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-029 | 33 | Test Outcome Screen, downloads, Practice Mode changes; check consensus/deadlock/regression; fix integration issues | 2026-09-10 | 2026-09-13 | Bhagyashree | Integration Test | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-032 | 34 | Agile tracker progress updates across all 4 milestones | 2026-09-10 | 2026-09-13 | Bhagyashree | Others | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-033 | 35 | Milestone 4 technical report compilation | 2026-09-10 | 2026-09-13 | Bhagyashree | Others | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-034 | 36 | Extend downloadable Transcript & Summary Report functionality to AI-vs-AI mode | 2026-09-10 | 2026-09-13 | Bhagyashree | Build | 3- Completed | 3 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-035 | 37 | Verify updated AI-vs-AI & Practice Mode flows post-M4 (Outcome screen, consensus, final allocation, concession analysis) | 2026-09-10 | 2026-09-13 | Bhagyashree | System Test | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-036 | 38 | Push milestone4-progress branch to main; update README | 2026-09-10 | 2026-09-13 | Bhagyashree | Others | 3- Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-037 | 39 | Test M4 Part 2 (Practice Mode) - verify chat-first UI, side panel, downloadable transcript/summary | 2026-09-11 | 2026-09-11 | Prasad | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-038 | 40 | Implement MongoDB persistence (Motor/PyMongo); create /api/history endpoints for negotiation storage/deletion; set up history UI integration | 2026-09-13 | 2026-09-13 | Harshita | Build | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-039 | 41 | Complete accompanying UI changes for history/DB integration | 2026-09-14 | 2026-09-15 | Harshita | Coding | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-040 | 42 | Fix MongoDB persistence issues; test negotiation/history APIs | 2026-09-13 | 2026-09-13 | Madhugna | Integration Test | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-041 | 43 | Implement History -> Negotiation Arena read-only replay, historical outcome, and report/summary downloads | 2026-09-14 | 2026-09-14 | Madhugna | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-042 | 44 | Improve UI - Current Proposal table, Available Resources, History/Replay flow, AI provider branding | 2026-09-15 | 2026-09-15 | Madhugna | Coding | 3- Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-043 | 45 | Postman testing of APIs on current main version | 2026-09-14 | 2026-09-15 | All | Integration Test | 2- In Progress | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-044 | 46 | Continue testing while DB integration work is added | 2026-09-14 | 2026-09-14 | Bhagyashree | System Test | 2- In Progress | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-045 | 47 | Prepare overall project report | 2026-09-14 | 2026-09-15 | Tharun Gowda | Others | 2- In Progress | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | day 4 | Needed alignment on which scenarios to pick among many options | Team discussion narrowed to 3 scenarios: vendor pricing, job offer, budget allocation
Sprint 1 | day 9 | Unclear negotiation flow/state model | Held architecture design session before module split
Sprint 2 | day 15 | Orchestrator turn-handling interface needed to be locked before dependent modules could start | Agreed interface contract between Harshita, Tharun Gowda, and Prasad before Sprint 2
Sprint 2 | day 21 | Persona schema needed finalizing before reasoning engine could be built | Madhugna finalized schema early in Sprint 2 for Tharun Gowda
Sprint 3 | day 23 | Deadlock detection depends on Orchestrator's state/round tracking being complete | Confirmed state tracking was logging correctly before starting Deadlock module
Sprint 3 | day 26 | Practice Mode's real-time AI reactions needed reasoning engine to already handle live input | Coordinated timing between Sree Priya and Tharun Gowda's tuning work
Sprint 3 | day 28 | Sree Priya was unwell during Sprint 3 and could not complete her Practice Mode tasks | Madhugna, Prasad, and Bhagyashree split her part among themselves to keep Sprint 3 on track
Sprint 4 | day 29 | Only 2 of 6 members (Bhagyashree, Sree Priya) were available to complete Milestone 4 work | Bhagyashree covered Outcome Screen (Part 1) and Testing & Integration (Part 3); Sree Priya covered Practice Mode UI + Downloads (Part 2); Bhagyashree also completed the technical report and updated Agile tracker progress for all 4 milestones
Sprint 5 | day 32 | Database/history persistence work (MongoDB) had not been started before the team moved to main branch integration | Harshita took up MongoDB Atlas/database integration on main; Madhugna fixed related persistence issues and added history/replay features; Madhugna and Prasad started Postman testing while the team continued functional testing in parallel

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-29 | 2026-07-29 | All | Documenting architecture decisions as we go | Jumping into modules before interfaces were agreed | Discussing scenarios collaboratively | Locked scenario list and architecture before module split
2 | Sprint 2 | 2026-08-01 | 2026-08-01 | Harshita,Prasad | Testing Orchestrator early with dummy agents | Building turn logic without confirming interface first | Leading integration testing | Finalized turn-handling contract before dependent builds
3 | Sprint 2 | 2026-08-06 | 2026-08-06 | Madhugna | Sharing config schema early with dependents | Delaying persona schema handoff | Refining screen from real feedback | Finalized schema ahead of Tharun Gowda's reasoning engine work
4 | Sprint 3 | 2026-08-29 | 2026-08-30 | Bhagyashree | Wiring live data incrementally | Building UI fully disconnected from backend | Keeping UI in sync with Orchestrator state | Aligned live agent turn rendering with Orchestrator's round tracking
5 | Sprint 3 | 2026-09-02 | 2026-09-07 | Madhugna, Prasad, Bhagyashree | Cross-covering tasks when a teammate is unwell | Leaving single-owner tasks with no backup plan | Quick redistribution of blocked work | Split Sree Priya's Practice Mode tasks across three team members to keep Sprint 3 on schedule
6 | Sprint 4 | 2026-09-10 | 2026-09-13 | Bhagyashree, Sree Priya | Splitting final-milestone work clearly into independent parts early | Relying on full team availability close to the deadline | Keeping the Agile tracker and documentation updated alongside development | Completed Outcome Screen, Practice Mode + Downloads, and full Testing & Integration despite reduced team availability; tech report and full Agile progress log completed by Bhagyashree
7 | Sprint 5 | 2026-09-13 | 2026-09-15 | Harshita, Madhugna, Bhagyashree | Starting database/persistence work earlier alongside feature development | Leaving API/DB testing (Postman) until after merge to main | Merging feature branches into main with updated documentation before starting new work | MongoDB Atlas integration, history/replay feature, and UI polish completed on main; Postman testing now underway across the team